## Risk Matrix
RISK MATRIX
Core Digital Transformation for Retail Banking — Enterprise Architecture & Regulatory Compliance Initiative
Date: February 18, 2026 ¦ Version: 1.0 ¦ Prepared By: System & Solutions Architect
THREAT MATRIX (Probability × Impact)
Probability ↓ / Impact → | Impact 1 (Minor) | Impact 2 (Low) | Impact 3 (Moderate) | Impact 4 (High) | Impact 5 (Critical)
Prob 5 (Almost Certain) | Score: 5 | Score: 10 | Score: 15 | Score: 20 | Score: 25
Prob 4 (Likely) | Score: 4 | Score: 8 | Score: 12 | Score: 16 R2 | Score: 20 R1
Prob 3 (Possible) | Score: 3 | Score: 6 | Score: 9 R3 | Score: 12 | Score: 15
Prob 2 (Unlikely) | Score: 2 | Score: 4 | Score: 6 | Score: 8 | Score: 10 R5, R6
Prob 1 (Rare) | Score: 1 | Score: 2 | Score: 3 | Score: 4 | Score: 5
OPPORTUNITY MATRIX (Probability × Positive Impact)
Probability ↓ / Impact → | Impact 1 (Minor) | Impact 2 (Low) | Impact 3 (Moderate) | Impact 4 (High) | Impact 5 (Critical)
Prob 5 (Almost Certain) | Score: 5 | Score: 10 | Score: 15 | Score: 20 | Score: 25
Prob 4 (Likely) | Score: 4 | Score: 8 | Score: 12 | Score: 16 | Score: 20
Prob 3 (Possible) | Score: 3 | Score: 6 | Score: 9 | Score: 12 | Score: 15
Prob 2 (Unlikely) | Score: 2 | Score: 4 | Score: 6 | Score: 8 R4 | Score: 10
Prob 1 (Rare) | Score: 1 | Score: 2 | Score: 3 | Score: 4 | Score: 5
RISK SUMMARY — ALL RISKS MAPPED
Risk ID | Risk Title | Category | Probability | Impact | Score | Risk Level | Matrix Position
R1 | KYC API SLA Violation | Threat | 4 | 5 | 20 | HIGH RISK | THREAT MATRIX (4,5)
R2 | Legacy System Integration Failure | Threat | 4 | 4 | 16 | HIGH RISK | THREAT MATRIX (4,4)
R3 | CI/CD Pipeline Breakdown | Threat | 3 | 3 | 9 | MEDIUM RISK | THREAT MATRIX (3,3)
R4 | Positive Stakeholder Adoption | Opportunity | 2 | 4 | 8 | HIGH OPPORTUNITY | OPPORTUNITY MATRIX (2,4)
R5 | Regulatory Non-Compliance | Threat | 2 | 5 | 10 | MEDIUM RISK | THREAT MATRIX (2,5)
R6 | Cybersecurity Breach During Migration | Threat | 2 | 5 | 10 | MEDIUM RISK | THREAT MATRIX (2,5)
R7 | Budget Overrun Due to Scope Creep | Threat | 3 | 3 | 9 | MEDIUM RISK | THREAT MATRIX (3,3)
LEGEND
High Risk (Score ≥ 15)
Medium Risk (Score 9–14)
Low Risk (Score < 9)
Opportunity