## Risk Register
RISK REGISTER
Core Digital Transformation for Retail Banking — Enterprise Architecture & Regulatory Compliance Initiative
Date: February 18, 2026 ¦ Version: 1.0 ¦ Prepared By: Business Analyst / Project Manager ¦ Status: Active
Risk ID | Risk Title | Category | Cause | Event | Impact Description | Probability (1–5) | Impact (1–5) | Risk Score (P × I) | Trigger / Early Warning Sign | Response Strategy
R1 | KYC API SLA Violation | Threat | Third-party provider latency or service downtime | Delay in customer onboarding and account activation | Compliance risk, reputational damage, customer churn | 4 | 5 | 20 | Missed onboarding logs or delayed provider API response beyond SLA threshold | Implement provider SLA monitoring with automated escalation matrix; establish fallback identity verification provider
R2 | Legacy System Integration Failure | Threat | Outdated APIs and schema mismatches between legacy and modern systems | Transactional errors, data inconsistency, or data loss during migration | Project delay, rollback required, additional cost, potential compliance exposure | 4 | 4 | 16 | Failed data validation checks between legacy and modern system environments | Conduct sandbox integration tests and version control audits; enforce phased cutover with parallel-run validation
R3 | CI/CD Pipeline Breakdown | Threat | Inadequate rollback automation or pipeline misconfiguration | Deployment failure causing production outage or failed sprint releases | System downtime, failed sprint releases, SLA breach on 99.9% uptime commitment | 3 | 3 | 9 | Build errors, test failures, or unresponsive staging environments detected during CI/CD run | Enhance automated rollback scripts; add pre-deployment quality gates and canary deployment validation
R4 | Positive Stakeholder Adoption | Opportunity | Intuitive UX workflows, dashboards, and effective change management | Increased staff and customer engagement with the new digital platform | Accelerated feedback loops, smoother rollout, higher NPS, reduced training cycles | 2 | 4 | 8 | Early user feedback praising UX design and positive adoption metrics from sandbox testing | Highlight success stories internally; promote adoption features through champions programme and recognition of early adopters
R5 | Regulatory Non-Compliance During Transition | Threat | Incomplete compliance controls or gaps during system cutover | KYC, AML, PCI-DSS, or GDPR audit findings during or after migration | Regulatory penalties, project halt, reputational damage, potential enforcement action | 2 | 5 | 10 | Compliance dashboard alerts showing unresolved audit findings or missed control checkpoints | Continuous compliance monitoring with dedicated CCO oversight; zero-exception policy on all compliance milestones
R6 | Cybersecurity Breach During Migration | Threat | Elevated attack surface during cloud migration window | Unauthorised access or data exfiltration during transition period | Data breach, regulatory penalties, severe reputational damage, financial loss | 2 | 5 | 10 | SOC anomaly detection alerts; unexpected access patterns in audit logs | Zero-trust security posture; penetration testing prior to go-live; 24/7 SOC monitoring throughout migration
R7 | Budget Overrun Due to Scope Creep | Threat | Uncontrolled scope changes or underestimated complexity | Project costs exceed approved budget of USD $7,920,000 | Project delays, reduced deliverables, executive escalation, resource reallocation | 3 | 3 | 9 | Change requests exceeding 10% of sprint capacity or budget variance warnings in project dashboards | Strict change control process requiring executive approval for all scope changes; weekly budget variance reviews
RISK SCORING LEGEND
High Risk (Score ≥ 15)
Medium Risk (Score 9–14)
Low Risk (Score < 9)
Opportunity