## Network Diagram
Activity ID | Activity Name | Predecessor | Duration | Phase
1.1.1 | Identify stakeholders | - | 1 Week | Planning
1.1.2 | Gather requirements | 1.1.1 | 1 Week | Planning
1.1.3 | Design cloud-native architecture | 1.1.2 | Concurrent (within 2 Weeks) | Planning
1.2.1 | Configure CI/CD Pipeline | 1.1.3 | 2 Months | Execution
1.2.2 | Integrate Core Banking & API Layers | 1.2.1 | 3 Months | Execution
1.2.3 | Test Compliance (KYC/AML/PCI-DSS) | 1.2.2 | 1 Month | Execution
1.3.1 | Deploy to Production | 1.2.3 | 0.5 Month | Closure
1.3.2 | Conduct User Training | 1.3.1 | 0.5 Month | Closure
1.3.3 | Perform Handover to Operations | 1.3.2 | 0.5 Month | Closure
Total Project Duration |  |  | 9.5 Months