## Risk Register
Risk ID | Risk Description (Cause-Event-Impact) | Probability (1-5) | Impact (1-5) | Risk Score (P x I) | Risk Type | Trigger | Response Strategy
R1 | Dependency on third-party onboarding/API provider may cause service delays impacting customer onboarding uptime | 4 | 5 | 20 | Threat | Missed onboarding logs or delayed provider response | Implement provider SLA monitoring with escalation matrix
R2 | Legacy and modern system integration complexity may cause data inconsistencies affecting compliance reporting | 4 | 4 | 16 | Threat | Failed data validation between legacy and modern systems | Conduct sandbox integration tests and version control audits
R3 | CI/CD pipeline instability may cause deployment failures delaying production releases | 3 | 3 | 9 | Threat | Build errors or unresponsive test environments | Enhance rollback scripts and add pre-deployment quality checks
R4 | Positive user adoption of new UX may increase digital engagement and product uptake | 2 | -4 | -8 | Opportunity | Early user feedback praising UX design | Highlight success stories internally and promote adoption features