## Threats
Template: Threats
Project:
P | 5 | [5 empty] | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1
B | [6 empty] | R2
A | 3 | [5 empty] | R3
B | [6 empty] | R4
I | 2 | [5 empty] | R5
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25

## Opportunitities
Template: Opportunities
Project:
P | 5 | [5 empty] | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1
B | [6 empty] | R2
A | 3 | [5 empty] | R3
B | [6 empty] | R4
I | 2 | [5 empty] | R5
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25

## Lab 50 Threats Sol
Example: Lab 50 Threats Solution
Project: Office Renovation Project
P | 5 | [5 empty] | Top 5 Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 |  |  |  | R2 | R1 | R1 | Aggressive Schedules | Compressed Milestones | Schedule Slippage | Ensure Adequate Resources
B | [6 empty] | R2 | Environmental | Dust and Fibers | Employee Health Suffers | Ensure Proper Filtration
A | 3 |  |  | R4 |  |  | R3 | Location | Stair Hazard | Safety Incidents | Designated Crew Elevator
B | [6 empty] | R4 | Construction Proximity | Noise/Disruptions | Lost Productivity | QC Partition Plans
I | 2 |  |  |  |  | R5 | R5 | Vendor | Low Commitment/Quality | Schedule Slips/Budget Overage | Careful Source Selection
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25
R3

## Lab 50 Opportunities Sol
Example: Lab 50 Opportunities Solution
Project: Office Renovation Project
P | 5 |  |  |  |  | R2 | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1 | Team Skill Sets | Experienced Facility Manager | Rapid Issue Resoltion | Incentives
B | [6 empty] | R2 | Budget | No constraints | Adequate Resources | Plan Accordingly
A | 3 | [5 empty] | R3
B | [6 empty] | R4
I | 2 | [5 empty] | R5
L | [6 empty] | R6
I | 1 |  |  |  |  | 2
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25
1
R1