## Template
Traceability Matrix Project: Date: Current
Requirement ID | Requirement Type | Requirement Description | Source / Stakeholder | Business Objective / Goal | Acceptance Criteria | Linked Functional / Non-Functional Requirement | Owner | Priority | Status | Verification Method | Related Risks | Comments / Notes
FR1 | Functional (FR) | Customers can securely onboard and manage accounts via web and mobile apps.
FR2 | Functional (FR) | Compliance staff can access real-time audit logs and KYC reports.
FR3 | Functional (FR) | Product owners can configure loan approval workflows and fraud detection rules.
FR4 | Functional (FR) | DevOps can automate builds, tests, and deployment pipelines.
NFR1 | Non-Functional (NFR) | Less than 2 seconds of average response time for all public-facing APIs.
NFR2 | Non-Functional (NFR) | The system must achieve 99.99% uptime across core services.
NFR3 | Non-Functional (NFR) | Encryption at rest and in transit must comply with bank-grade security policies.
NFR4 | Non-Functional (NFR)

## Instructions
Traceability Matrix Completion Instructions
Entry | Instruction | Example
Project Name | Mention the project or program name for context. | Secure Retail System Upgrade
Requirement ID | Assign a unique identifier to each requirement using sequential numbering. | 001
Requirement Type | Specify if the requirement is Functional or Non-Functional. | Functional
Requirement Description | Provide a clear, concise description of the requirement. | The system shall allow login through biometric authentication.
Source/Stakeholder | Identify the origin of the requirement (for example, stakeholder, workshop). | Operations Manager
Business Objective/Goal | Describe the business need or strategic objective supported by the requirement. | Improve security and user experience
Acceptance Criteria | Define the conditions under which the requirement will be accepted. | User logs in successfully via biometrics
Linked Functional/Non-Functional Requirement | List related or dependent requirements by referencing their IDs. | 003 (Performance)
Owner | Identify the person or team responsible for fulfilling the requirement. | IT Lead
Priority | Assign a priority level (e.g., High, Medium, Low). | High
Status | Track the progress (e.g., Not Started, In Progress, Blocked, Completed). | In Progress
Verification Method | Specify how the requirement will be verified (e.g., Testing, Inspection). | Testing
Related Risks | Identify risks associated with the requirement to assist in planning. | Security breaches
Comments/Notes | Capture additional information or ongoing discussions. | Biometric SDK vendor confirmed.

## Example
Traceability Matrix Project: Core digital transformation for a retail bank Date: 1 June 20xx
Requirement ID | Requirement Type | Requirement Description | Source / Stakeholder | Business Objective / Goal | Acceptance Criteria | Linked Functional / Non-Functional Requirement | Owner | Priority | Status | Verification Method | Related Risks | Comments / Notes
001 | Functional | The system shall allow login through biometric authentication. | Operations Manager | Improve security and user experience | User logs in successfully via biometrics | 003 (Performance) | IT Lead | High | In Progress | Testing | Security breaches | Biometric SDK vendor confirmed.
002 | Non-Functional | The app must support real-time inventory updates. | Supply Chain Head | Enhance operational efficiency | Inventory updates reflect within 2 seconds. | N/A | Product Manager | Medium | Not Started | Prototype Testing | System performance issues | Dependency on third-party API.
003 | Non-Functional | Biometric login must respond within 1 second. | Operations Manager | Provide seamless user experience | Login completes within 1 second. | 001 (Functional) | IT Lead | High | Not Started | Performance Testing | Delay in login may affect user adoption | Performance to be reviewed by IT team.
FR1 | Functional (FR) | Customers can securely onboard and manage accounts via web and mobile apps.
FR2 | Functional (FR) | Compliance staff can access real-time audit logs and KYC reports.
FR3 | Functional (FR) | Product owners can configure loan approval workflows and fraud detection rules.
FR4 | Functional (FR) | DevOps can automate builds, tests, and deployment pipelines.
NFR1 | Non-Functional (NFR)
NFR2 | Non-Functional (NFR)
NFR3 | Non-Functional (NFR)
NFR4 | Non-Functional (NFR)