## Network Diagram
NETWORK DIAGRAM & PROJECT SCHEDULE
Project: Core Digital Transformation for a Retail Banking
Date: February 18, 2026 ¦ Version: 1.0 ¦ Total Duration: 8.5 months
Task ID | Task Name | Phase | Duration | Predecessors | Start | End | Critical Path
1.1.1 | Identify Stakeholders | Planning | 3 days | - | Week 1 | Week 1 | Yes
1.1.2 | Gather Requirements | Planning | 1 week | 1.1.1 | Week 1 | Week 2 | Yes
1.1.3 | Design Cloud-Native Architecture | Planning | 1 week | 1.1.2 | Week 2 | Week 2 | Yes
1.2.1 | Configure CI/CD Pipeline | Execution | 1 month | 1.1.3 | Month 1 | Month 1 | Yes
1.2.2 | Integrate Core Banking & API Layers | Execution | 4 months | 1.2.1 | Month 1 | Month 5 | Yes
1.2.3 | Test Compliance (KYC/AML/PCI-DSS) | Execution | 2 months | 1.2.2 | Month 5 | Month 6.5 | Yes
1.3.1 | Deploy to Production | Closure | 2 weeks | 1.2.3 | Month 6.5 | Month 7 | Yes
1.3.2 | Conduct User Training | Closure | 3 weeks | 1.3.1 | Month 7 | Month 7.75 | No
1.3.3 | Perform Handover to Operations | Closure | 2 weeks | 1.3.1, 1.3.2 | Month 7.75 | Month 8.5 | Yes
PROJECT PHASE SUMMARY
Planning Phase | Duration: 2 weeks | Tasks: 3 | Sequential completion of stakeholder identification, requirements gathering, and architecture design
Execution Phase | Duration: 6 months | Tasks: 3 | CI/CD setup, core banking integration, and comprehensive compliance testing (KYC, AML, PCI-DSS)
Closure Phase | Duration: 1.5 months | Tasks: 3 | Production deployment, user training, and operational handover with support documentation
TOTAL PROJECT DURATION | 8.5 months | 9 tasks | Critical path includes all Planning and Execution tasks, plus Production Deployment and Handover
Critical Path Tasks:
The critical path represents the longest sequence of dependent tasks that determines the minimum project duration.
All tasks on the critical path must complete on schedule to avoid delaying the entire project.
User Training (1.3.2) can run in parallel with other closure activities and is not on the critical path.
TASK DEPENDENCY FLOW (NETWORK DIAGRAM)
┌─────────────────────────────────────────────────────────────────────────────────────┐ │ Planning Phase (2 weeks) │ │ ┌────────────┐ ┌────────────┐ ┌────────────────────────┐ │ │ │ 1.1.1 │ ───► │ 1.1.2 │ ───► │ 1.1.3 │ │ │ │ Identify │ │ Gather │ │ Design Cloud-Native │ │ │ │ Stakehold. │ │ Req. │ │ Architecture │ │ │ └────────────┘ └────────────┘ └────────────────────────┘ │ │ (3 days) (1 week) (1 week) │ │ └─────────────────────────────────────────────────────────────────────────────────────┘ │ ▼ ┌─────────────────────────────────────────────────────────────────────────────────────┐ │ Execution Phase (6 months) │ │ ┌────────────┐ ┌────────────────────────┐ ┌─────────────────┐ │ │ │ 1.2.1 │ ───► │ 1.2.2 │ ───► │ 1.2.3 │ │ │ │ Configure │ │ Integrate Core Banking │ │ Test Compliance │ │ │ │ CI/CD │ │ & API Layers │ │ (KYC/AML/PCI) │ │ │ └────────────┘ └────────────────────────┘ └─────────────────┘ │ │ (1 month) (4 months) (2 months) │ └─────────────────────────────────────────────────────────────────────────────────────┘ │ ▼ ┌─────────────────────────────────────────────────────────────────────────────────────┐ │ Closure Phase (1.5 months) │ │ ┌────────────┐ ┌────────────────┐ ┌───────────────────┐ │ │ │ 1.3.1 │ ───► │ 1.3.2 │ ───► │ 1.3.3 │ │ │ │ Deploy to │ │ Conduct User │ │ Handover to │ │ │ │ Production │ ┌─► │ Training │ ┌─► │ Operations │ │ │ └────────────┘ │ └────────────────┘ │ └───────────────────┘ │ │ (2 weeks) │ (3 weeks) │ (2 weeks) │ │ │ (parallel track) │ │ │ └───────────────────────┘ │ └─────────────────────────────────────────────────────────────────────────────────────┘ Legend: ───► Sequential dependency (must complete before next task starts) ┌─► Parallel track (can run concurrently with critical path)