## WBS
WORK BREAKDOWN STRUCTURE (WBS)
Project: Core Digital Transformation for a Retail Banking
Date: February 18, 2026 ¦ Version: 1.0
WBS Code | Task / Deliverable | Level | Description
1.0 | Core Digital Transformation for a Retail Banking | 0 | Complete digital transformation initiative to modernize retail banking systems with cloud-native architecture, regulatory compliance, and real-time data capabilities
1.1 | Planning | 1 | Project initiation, stakeholder engagement, requirements gathering, and architectural design
1.2 | Execution | 1 | Development, integration, testing, and compliance validation
1.3 | Closure | 1 | Production deployment, training, handover, and post-implementation support
1.1.1 | Identify Stakeholders | 2 | Identify and document all project stakeholders including CTO, Compliance Officer, DevOps engineers, Product Owners, customers, and regulators. Create stakeholder register and engagement plan.
1.1.2 | Gather Requirements | 2 | Conduct interviews and workshops with stakeholders to elicit functional and non-functional requirements. Document business requirements (BRD) and technical specifications.
1.1.3 | Design Cloud-Native Architecture | 2 | Design microservices architecture, containerization strategy, API gateway, data pipeline architecture, and security controls. Create architecture diagrams and technical design documents.
1.2.1 | Configure CI/CD Pipeline | 2 | Set up Jenkins/GitLab CI/CD pipelines for automated builds, tests, and deployments. Implement blue-green and canary deployment strategies with automated rollback capabilities.
1.2.2 | Integrate Core Banking & API Layers | 2 | Migrate legacy core banking systems to microservices. Develop secure API gateway for inter-service communication and third-party integrations (credit bureaus, payment gateways).
1.2.3 | Test Compliance (KYC/AML/PCI-DSS) | 2 | Conduct compliance testing for KYC identity verification, AML transaction monitoring, PCI-DSS cardholder data security, and GDPR data privacy controls. Validate audit logging and encryption.
1.3.1 | Deploy to Production | 2 | Execute production deployment using blue-green strategy. Perform smoke tests and health checks. Activate monitoring and alerting. Validate 99.99% uptime SLA and <500ms transaction latency.
1.3.2 | Conduct User Training | 2 | Deliver role-based training for customers, product owners, compliance officers, and DevOps engineers. Conduct competency assessments and provide training materials (guides, videos, runbooks).
1.3.3 | Perform Handover to Operations | 2 | Transfer ownership to operations team. Provide operational runbooks, incident response procedures, and escalation contacts. Conduct knowledge transfer sessions and establish support SLAs.
WBS SUMMARY
Total Project Components: | 13
Major Phases (Level 1): | 3 (Planning, Execution, Closure)
Total Tasks (Level 2): | 9 tasks
Estimated Project Duration: | 8.5 months (Planning: 2 weeks ¦ Execution: 6 months ¦ Closure: 1.5 months)